## Slide 1
GNIRS Quarterly Review #4
November 15, 2000

## Slide 2: Outline
Project summary
Flexure analysis report
Project management
Appendix A - Images
Appendix B - List of Released Drawings

## Slide 3: Project Summary
Progress overview
Budget and expenditures to date
Report on last QR plans

## Slide 4: Progress Overview
The delivery date of the instrument has not changed
  Still scheduled for July-August, 2002
The project is 39% complete
  We are about 1.5 months behind schedule overall
We have completed 45 of 225 total project milestones
The Systems Engineering effort is essentially complete
Software low-level code development is 56% complete
Mechanism fabrication has started
Bench fabrication is started
  OIWFS bench completes this month
  Pre-Slit bench is at a vendor
  Post-Slit bench releases this month
Electronics fabrication has started

## Slide 5: Project Status
Progress from August ’99
  Overall project 39%
  Management & Reporting 39%
  Systems Engineering 100%
  Mechanical 30%
    Benches 35%
    Mechanisms 39%
    Fixed Assemblies 7%
  Electronics 42%
  Software 27%
  Integration 0%
  Procurement 44%

## Slide 6: Project Costs
Baseline Estimate (Jan 99 to completion)
  Labor $3,391,232
  Capital $ 836,462
  Total $4,227,694
Current Forecast (revised 9/15/00)
  Labor $3,014,805
  Capital $ 806,250
  Total $3,821,055
Performance ratios
  BCWS = $ 1,431,064 (budgeted cost of work scheduled)
  BCWP = $ 1,074,179 (budgeted cost of work performed)
  ACWP = $ 928,176 (actual cost of work performed) (source: CAS)
  CPI = 1.16 (BCWP/ACWP)
  SPI = 0.75 (BCWP/BCWS)

## Slide 7: Planned Status by this Quarterly Review
Fabrication contract awards:
  all optical benches
  3 mechanisms
Complete 3D designs of all remaining mechanisms
Complete lens delivery and acceptance testing
All optics on order or delivered
Begin 3D design of 5 of the 16 fixed assemblies
Begin electronics fabrication
Begin OIWFS components integration
Rotary and linear prototype reports
Grating master ruling test report

## Slide 8: Task Status
Item | Status | Comments
Optical benches contracted | Complete - vendors selected | Fabrication completes next year
Have 3 of 8 mechanisms in fabrication | Complete - 3 mechanisms in fab or done: slit/decker, environmental cover and part of camera and filter wheel | 
Complete 3D design of remaining mechanisms | Not Complete – 3D Design of prism turret and focus mechanism complete | Will complete 3D design of grating turret, acquisition mirror and rest of camera by end of this quarter
Complete lens delivery and testing | Not complete - Delivery of BaF2 late | New lot ready in February, delivery in March
All optics on order or delivered | Not complete - Delayed by mechanism definition | All optics should be on order by December 15th
Begin 3D design of 5 fixed assemblies | Started - Thermal enclosure mount, front dewar shell, rear dewar shell, bulkhead, aft tangent bar | Will complete bulkhead assembly design by end of this year
Begin electronics fabrication | Started - Thermal enclosure and cables | Thermal enclosure should complete by Feb 01
Begin OIWFS integration | Not complete - Components delayed | Integration tentatively scheduled for January
Rotary & Linear Prototype testing | Complete - Results incorporated into designs | Will carry out flexure testing on camera drive assembly to verify design
Grating master ruling report | Complete - Documented in SDN | 

## Slide 9: Systems Engineering
Flexure Analysis:
  Completed 10/00
  Results show no need for active compensation
    Passive compensation via collimator mount required
    Analysis will be used to guide mount design (later this year)
All further analysis is in support of detailed design

## Slide 10: Flexure Analysis
NASTRAN Model
  Design presented 8/00
  Mechanisms, optics modeled as rigid bodies (reasonable assumption)
  Tilts and displacements calculated for 3 orthogonal gravity vectors
  Some subsequent modifications
    Stiffened high-flexure areas identified by model
    Verified all mechanism interfaces
    Changes in flexure should be modest; expected but not required to improve

## Slide 11
Instrument Assembly F.E.A. Model Deformed shape scaled by 7500x loading; gravity in the –y direction; scale in inches.
10m
Note: Much of the Offner deflection is due to rigid body motion of the assembly with respect to its support bulkhead, and will not contribute image decenter.

## Slide 12
Instrument Assembly F.E.A. Model Deformed shape scaled by 7500x loading; gravity in the –x direction; scale in inches.
14m

## Slide 13
Instrument Assembly F.E.A. Model Deformed shape scaled by 7500x loading; gravity in the –z direction; scale in inches.
5m

## Slide 14: Flexure Analysis
Optical Model
  Calculations done independently with 2 programs by E. Pearson and M. Liang: good agreement
  Optics laid out in absolute coordinates
  Tested with rigid-body rotation of spectrograph (should have no net effect)
  Apply NASTRAN tilts/displacements to optical elements

## Slide 15: Optical Ray Trace
Red ray: Spectrograph
Blue ray: On-Instrument Wave Front Sensor

## Slide 16: Flexure Analysis
Results - WFS to Slit
  Differential flexure of WFS relative to slit should keep star centered on slit to <10 m during 1 hour
  Calculated shifts in microns for 1 gravity:
  Worst case for 1 hour ~5 m shift
  Meets specification comfortably
Gravity x y
-y -14.4 -9.0
x -1.7 -5.3
z -10.7 -0.4

## Slide 17: Flexure Analysis
Results - Slit to Detector to Slit
  Differential motion between slit/star and detector should keep image centered to 2.7 m (0.1 pixel) during 1 hour
    Motion of slit image in dispersion direction (z)
    Motion of star image along slit (y) (motion of slit image similar)
  Calculated shifts in microns for 1 gravity:
Gravity z y
-y -13.1 -14.6
x 1.3 3.5
z -24.2 3.5

## Slide 18: Flexure Analysis
Results - Slit to Detector to Slit (2)
  Worst case 1 hour in z = 7.2 m; worst case in y = 4.0 m
  Design collimator mount to provide passive compensation for 2 largest components
    Worst case in y now 1.8 m in 1 hour (meets spec)
    Worst case in z now 3.7 m in 1 hour (factor of 1.4)
  Analyze final bench design to guide collimator mount design

## Slide 19: Project Management
Project Status
Problems and Concerns
Schedule & Planning
Milestones
Budget and Expenditures
Labor and Capital Projections
Project Organization
Plans for Next Review

## Slide 20: Mechanical Status #1
Bench design and analysis
  Bench flexure analysis is complete
  Large plate has been cut
    Distributed to vendors with drawing packages
  All benches in fabrication as of 11/20
    OIWFS bench released 9/20; fabrication completes 11/23
    Pre-Slit bench released on 9/20; 10% complete
    Post-slit bench drawings will be released 11/20
Mechanism designs in process
  Camera turret assembly
  Acquisition mirror assembly
  Focus mechanism assembly
  Grating turret assembly
  Prism turret assembly

## Slide 21: Mechanical Status #2
Mechanism components currently in fabrication
  Camera hub spindle and drive assembly
  Camera barrels
  Slit/Decker
  Filter wheel assembly
  Mechanism common components
    Motor drive assembly
  Cryo heads/lines
    Will be ordered in March 2001

## Slide 22: Electronics Status
Design activities
  Component controller thermal enclosure design completed
  Hard-stop circuit required for the mechanisms and the Phytron drivers has been designed and the schematics finished
  A scale model GNIRS for harnessing design has been completed
  Dewar, mechanisms and OIWFS cabling
    These cabling issues are being addressed thru the scale model GNIRS
      cable routing and possible intermediary connectors
      how to route cables around the Bench and thru the Radiation Shields
  A complete GNIRS thermal enclosure parts list has been prepared
Fabrication in progress
  Thermal enclosure wiring and assembly
  Dewar and shield interface PCB’s
  Connectors and boards on order

## Slide 23: Software Status
Component Controller code 56% complete
High level (EPICS) code 7% complete
  Waiting for completion of the electronics thermal enclosure
  The next phase is actual testing of component controller code
    Motor drive and mechanism status/position sensing

## Slide 24: Optics Status
Lenses and Windows
  Large lenses & windows in fabrication with RMI; 11 of 18 accepted
  Only BaF2 lenses for short red and blue cameras remain
    Two lots of BaF2 material have failed so far; a third lot is in process
  Pupil viewer lenses ordered and received
Mirrors
  Flat mirrors to be ordered as individual mechanism design proceeds; 2 aluminum substrates & 7 glass substrates
Gratings
  Master rulings complete and tested
  Grating replicas to be ordered by 12/15/00
Filters
  7 filters ordered through UH consortium; 2 failed spec and vendor is expected to replace
Prisms
  Prisms to be ordered by 12/15/00

## Slide 25: Phytron Motor Status
Motor qualification initiated
  Tested 4 motors, 3 out of 4 failed
  Phytron is replacing all 12 motors
    Delivery of first 4 replacements expected 11/15/00
    Qualification will proceed after delivery
    2 Gemini spare motors available on loan; these will support mechanism cold testing until motors pass muster

## Slide 26: Problems and Concerns
OIWFS component late delivery
  Will cause resources to be diverted from other activities to work on OIWFS integration and test
  Filter wheel will arrive untested
  Focus assembly now in NIRI has been promised to us for January 2001
Completing bench fabrication without major rework
  Contingency time to re-fabricate a bench component is marginal
Camera drive assembly flexure testing still pending
  Design modifications may affect turret drive designs on three mechanisms
Completion of the RMI camera optics order
  BaF2 material lot failures have caused a significant delay in completing the order
    Over 130 days required to grow a new lot
    We are working to assist RMI in procuring material
Firm quotes and schedules on prisms still pending

## Slide 27: Three Phases of the Project
| Aug 99 – Feb 00 | Mar 00 – Jun 01 | Jul 01 – Jul 02 |
Analysis & Prototyping
Pre-Fab Review
Design/Fab/Test
Mid-Fab Review
Integration & Test

## Slide 28: Summary Plan

## Slide 29: Project Plan – Sheet 1

## Slide 30: Project Plan – Sheet 2

## Slide 31: Project Milestones by Quarter
As of 11/3/00

## Slide 32: Milestones since PFR (5/00)

## Slide 33: Planned vs Actual Expenditures

## Slide 34: Capital and Labor Comments
The capital reported is as of 11/3/00
Some capital expenditures have been charged to procurement instead of the respective WBS number
The labor histogram shows the result of shared resources, utilizing fewer instrument makers and subcontracting work vs. doing it in-house
Capital expenditures are expected to increase substantially in the next two quarters

## Slide 35: Planned vs Actual Expenditures
WBS Title Total Planned Actual
Plan to date to date
5.0 GNIRS Total $3,821,055 $1,393,694 $1,341,448
5.1 Management $1,149,627 $ 426,427 $ 396,138
5.2 Systems Eng $ 232,982 $ 220,218 $ 263,250
5.3.1 Mechanisms $ 951,854 $ 380,589 $ 255,816
5.3.2 Bench Assemblies $ 303,037 $ 119,142 $ 59,418
5.3.3 Fixed Assemblies $ 501,174 $ 23,227 $ 14,895
5.4 Electronics $ 146,366 $ 43,640 $ 35,957
5.5 Software $ 108,802 $ 16,243 $ 32,339
5.6 Integration $ 201,960 $ 0 $ 0
5.7 Deliverables $ 37,164 $ 0 $ 0
5.8 Procurement $ 188,090 $ 164,152 $ 295,232

## Slide 37
Jan 99

## Slide 38
$806,250
$759,192
Jan 99

## Slide 39: GNIRS Project Organization
Gemini Projects
Project Manager
N. Gaughan
Director, NOAO
S. Wolff
Project Assistant
D. Eklund (.5)
Administrative Assistant
M. Bowersock
Project Scientist,
Systems Engineering
J. Elias
Mechanical Engineers
E. Hileman
G. Muller
Electrical Engineer
J. Penegor
Optical Engineer
M. Liang
Procurement & Vendor Liaison
A. Davis
Software
R. Wolff
Support Scientists
D. Joyce (.5)
[B. Gregory]
Mechanical Designers
J. Andrew
D. Rosin
E. Downey
R. Robles
D. Circle
Electrical Technicians
R. George
Staff Added: R. George/ D. Circle
Staff Transferred: No changes
Updated 11/1/00
General Technician
J. Pina (.5)
Programmer
P. Ruckle
Instrument Maker
J. Stein

## Slide 40: Plans for Next Review
The Next Quarterly Review will be held in the February-March timeframe
The project expects to make significant progress in fabrication
  All benches complete
  All remaining mechanisms will be in fabrication
All optics on order
  Flats/Prisms/Grating replicas
Design effort will concentrate on fixed assemblies
  Bulkhead assemblies
  Dewar components
  Mounting trusses
  Cryo hardware
Electronics TE fabrication should be completed
Software testing should be in process
OIWFS components integration/test should be underway

## Slide 41: Appendix A - Images

## Slide 42: Wave Front Sensor Bench Rendering

## Slide 43: Wave Front Sensor Bench in Fab

## Slide 44: Wave Front Sensor Bench Rendering

## Slide 45: Wave Front Sensor Bench in Fab

## Slide 46: Wave Front Sensor Bench Cover

## Slide 47: Camera Turret Hub Assembly

## Slide 48: Camera Turret - Fabricated

## Slide 49: Pre-Slit Bench Assembly

## Slide 50: Pickoff/Fold Mirror Assembly

## Slide 51: Prism Turret Assembly

## Slide 52: Prism Turret Hub Assembly

## Slide 53: Appendix B – List of Released Drawings

## Slide 54: List of Released Drawings

## Slide 55: List of Released Drawings

## Slide 56: List of Released Drawings

## Slide 57: List of Released Drawings

## Slide 58: List of Released Drawings

## Slide 59: List of Released Drawings