## Slide 1
QUARTERLY REVIEW
January 24, 2002

## Slide 2: Agenda
0830 QR - Project Overview
0930 break
0945 QR - Technical Progress
1045 Break
1100 QR - Management
1200 Lunch
1300 Tour of design area workstations
1330 Hardware tour
- Instrument Shop
- EE Lab
- Blue Room
1400 Software - Hardware Demo

## Slide 3: GNIRS Quarterly Review
Table of Contents
Introduction Pg 4
Project Summary Pg 6
Configuration & Integration Pg 23
Project Management Pg 43
Appendices Pg 64

## Slide 4: Introduction
This is the 7th GNIRS Quarterly Review
GNIRS is in the final design and fabrication phase
  All bench assemblies are complete
  Bulkhead and Dewar Shell assemblies are complete
  Mechanism fabrication is complete
  Mechanism testing is underway
  OIWFS integration is complete except for the detector
We are on track for delivery in October of 2002

## Slide 5: Outline
Project summary
  Last QR Response
  Progress Overview
  Cost and Schedule Status
Problems and Concerns
Configuration Update
Technical Progress
Project management
Plans for next review

## Slide 6: Project Summary
Response to last QR report
Progress overview
Summary schedule
Work left
Budget and expenditures to date

## Slide 7: Response to October QR - Issues to be Reviewed
Completion of items
  OIWFS integration
  Lens delivery/testing
  Mechanism fabrication
  Mechanism/optical testing
  Fixed Assy 3D/2D design
  TE fabrication
  Bulkhead fabrication
  Dewar component fabrication
  Optics procurement
ATP (Plan)
Design delays
  Radiation Shields
Rework items
OIWFS issues
IFU late delivery
Change orders
Documentation approach

## Slide 8: Task Status
ITEM | STATUS | COMMENT
OIWFS component integration | Complete – Detector installation on hold | Waiting for Gemini decision on prism. February cut-off date.
Lens delivery/testing | Complete | 
Mechanism fabrication | Complete | Some rework in process
Mechanism/optical testing | Not Complete – delayed because of fabrication delays | Should complete in March
Fixed Assembly 3D/2D design | Not Complete – Radiation shields still in process | Completion expected in January
TE fabrication | Complete | 
Bulkhead fabrication | Complete | Fit checks complete except for radiation shields
Dewar component fabrication | Complete | 
Optics procurement | Not Complete – Simulator optics not yet purchased | Simulator is in design stage. Not a pacing item. Rescheduled to a later date.

## Slide 9: Response to October QR
Planned Completions by this Quarterly Review
  3D and 2D design of all fixed assemblies
  Fabrication of all mechanisms
  Fabrication of the Bulkhead Assembly
  Mechanical fabrication except for:
    Rework items
    Shipping container
    Items associated with flexure testing
  Mechanism and optical subassembly testing
  Receive all optics
  Electronics fabrication and checkout except for:
    Some cables
    Rework items
  Initial software coding
  Component controller software testing
  OIWFS component integration
  Change orders for Chile Delivery and for Differential Pressure Switch
  Manual outlines

## Slide 10: Response to October QR
ATP
  A draft of the ATP and commissioning plan was submitted to Gemini for review; returned with minor comments last week
Change Orders are in process
  For Chile delivery
  For the Differential Pressure Switch
Manual outlines
  Maintenance Manual in process
  Software and Operation manuals are not started

## Slide 11: Response to October QR
Software coding
  Component controller software
    Coding is complete
    Checkout complete as far as can be done without actual hardware to exercise
    All checks with the electronics are complete
  EPICS software is 95% complete
IFU late delivery
  Proceeding with mass modules
  We will try to integrate the IFU when it becomes available

## Slide 12: Summary Project Plan

## Slide 13: Revised Bench Integration Plan

## Slide 14: Work Left – Integration Plan
Two critical areas
  Radiation shields
  Mechanism testing
Need passive shields first so bulkhead can be assembled and wired
Active shields needed for integration of bench into dewar
Key resources
  Electrical technician for wiring
  M&P engineer and technician for cleaning and prep work
  Scientists for testing
  Mechanical engineers and designers for shields
  Instrument makers for assembly/rework/testing

## Slide 15: Project Status - Progress from August ’99
  WBS element Mar June October January
  5.0 Overall project 53% 66% 80% 86%
  5.1 Management & Reporting 51% 61% 71% 80%
  5.2 Systems Engineering 100% 100% 100% 100%
  5.3 Mechanical 52% 70% 87% 94%
  5.3.1 Mechanisms 66% 84% 92% 97%
  5.3.2 Benches 55% 70% 100% 96%
  5.3.3 Fixed Assemblies 16% 36% 62% 84%
  5.4 Electronics 63% 59% 86% 71%
  5.5 Software 49% 63% 85% 86%
  5.6 Integration 0% 0% 2% 23%
  5.7 Deliverables 0% 0% 0% 45%
  5.8 Procurement 54% 67% 77% 86%

## Slide 16: Progress Overview
The delivery date of the instrument is now October 24, 2002
  Delay radiation shield design
  Delay in mechanism testing
The project is currently 86% complete overall
We have completed 170 of 226 total project milestones
Our critical path(s) are
  Radiation Shields: 3D and 2D design and fabrication
  Mechanism testing
Electronics fabrication left is mechanism and dewar wiring
Software Component Controller code is essentially complete

## Slide 17: Focus of Last Quarter of Work
Design/fabrication activity concentrated on
  Radiation shield design
  Bulkhead Assembly fabrication/acceptance tests/fit checks
  Fit checks and fixes
  Mechanism warm tests, flexure tests, rework
  Assembly cleaning and wiring, prep for integration and/or cold testing
  Final fixed assembly fabrication: trusses, etc.
  Telescope simulator design
  General design cleanup (configuration control)
Procurement
  Mechanical
  Optical

## Slide 18: Progress and Schedule Comments
Mechanical design virtually complete
  Radiation Shields and the Thermal Distribution Assembly remain
Fabrication will continue through March on shields
Sub-assembly flexure testing complete
Mechanism fabrication is essentially complete
  Minor rework in process
    Focus mechanism
    Prism turret
  Filter wheel cleaned and wired, ready for final warm test
  Grating Turret ready for cleaning and wiring
  Camera cleaning and wiring in progress

## Slide 19: Budget and Expenditures
Baseline Estimate (Jan 99 to completion)
  Labor $3,391,232
  Capital $ 836,462
  Total $4,227,694
Current Forecast (Jan 99 to completion)
  March June October January
  Labor $2,866,775 $3,002,938 $2,957,389 $2,986,915
  Capital $1,074,798 $1,181,900 $1,138,285 $1,384,670
  Total $3,941,573 $4,184,838 $4,095,674 $4,371,585
Performance ratios
  March June October January
  BCWS $1,754,979 $2,863,855 $3,085,811 $3,263,216
  BCWP $1,611,542 $2,011,383 $2,526,319 $2,899,362
  ACWP $1,742,651 $2,113,212 $2,762,963 $3,339,222
  CPI 0.92 0.95 0.91 0.89
  SPI 0.92 0.70 0.82 0.87

## Slide 20: Problems and Concerns
Top level integration has been delayed by 2 months until April 1st
  Radiation shield design taking longer than expected
  Mechanism rework required to pass flexure tests and fit checks
  Focus mechanism design/fab/assembly took longer than expected
Radiation shield fabrication will extend into March
Documentation (Manuals)
  Maintenance manual outline started; procedures documented as carried out
  delayed by focus on mechanism testing and radiation shields
OIWFS prism installation
  OIWFS complete except for installing detector
  prism needs to be installed and tested before benches integration into the dewar – latest date for receipt is 3/4/2002 (with installation hardware)
IFU
  Proceeding with mass models
  There is a chance for integration if it arrives in February

## Slide 21
This Page Intentionally Left Blank

## Slide 23: GNIRS Configuration
Most design work complete
Remaining work as “punch list”

## Slide 25: Shield Status
Passive shields (2 sets)
  3D design complete
  Detailing in progress
  Fabrication proceeding as design completes
Active shields
  3D design in progress
  Accurate weight estimate possible

## Slide 26: Active Shield

## Slide 27: Passive & Active Shields (exploded)

## Slide 28: Weight Budget
Revised Value = 4052 lb
  limit = 4409 lb
  increase 56 lb from last QR, -61 lb from 3/01
  change mainly due to shields, hence only small c.g. change
Spot check hardware against models
  true weights within 2% of models

## Slide 29
This Page Intentionally Left Blank

## Slide 31: Subsystem Testing
Basic philosophy remains unchanged
  All subsystems tested prior to integration
  Quantify performance for mechanism motion tables, flexure compensator

## Slide 32: Subsystem Testing (2)
All mechanisms have undergone functional testing
  Some testing on focus remains (1/17)
  Need to complete clean/cold tests
  Turrets flexure performance determined, provides initial input for flexure compensator settings
Optical tests on camera, collimator remain
  No alignment required
  Fore-optics aligned and tested

## Slide 33: Subsystem Testing (3)
OIWFS integration nominally complete
  System aligned and tested with warm MUX
  Need to install science detector
  Still limited time to install and check S-H prism

## Slide 34: OIWFS Issues
All OIWFS software accounted for
MUX readout working
Some setup information incomplete
Electronics documentation incomplete
Operating software is working
Mechanism status (9/20/01)
  Zero is displaced on gimbal Y-axis
  Otherwise, hardware appears OK

## Slide 35: Software Components
Top Level
  Instrument Sequencer
  Interfaces to detector, wavefront sensor, components controller, OCS
Components Controller
  Control (CAD, CAR, Apply)
  Status and Alarm database (SAD)
Low Level Software
  Motor control
  Temperature readback
  Pressure monitoring

## Slide 36: Software Work Remaining - Design
Alarm and Status Propagation
  Complete
WCS/DHS header information
  If necessary

## Slide 37: Software Work Remaining - Coding
Low Level (Hardware Interfacing)
  No remaining coding planned
Components control
  Tweak engineering user interface
Instrument Sequencer and Interfaces
  Engineering User interface (ongoing)

## Slide 38: Software Work Remaining - Testing
Low Level
  Prefer fully wired system for end-to-end test
  Motors
    Multiple motors simultaneously
    Determine distances between limits, switches, etc
    Set speeds, acceleration, backlash parameters
    Actual mechanism(s) needed
  Temperature Probes
    Set calibration curve and individual offsets
  Pressure Sensor
    Verify operation in final configuration

## Slide 39: Software Work Remaining - Testing
Upper Level -- EPICS
  Engineering screens provide next level of test
Top Level -- OCS compliance
  use OCSwish
    new tool, in use in Hawaii, verifies OCS interface

## Slide 40: Software Work Remaining
Simulation allows testing without hardware
  Works only for motors.
Additional work
  Lab Support
  Conversion to GEM7 or GEM8
  powerPc on Detector controller
  Mechanism testing
    Set configuration files

## Slide 41: Software Work Remaining
Software is done when
  Motors, temperature readback, etc, work at command line (low level)
  Engineering Screens provide required control and readback
  OCSwish/Acceptance test proves compliance with Gemini system
  GNIRS works on the telescope

## Slide 42: Software Interface Issues
Array Controller
  Interfaced correctly to instrument sequencer?
OCS
  OCSwish will help, but it’s new to us
OIWFS
  real testing is not GNIRS concern.

## Slide 43: Project Management
Project Status
Schedule & Planning
Milestones
Budget and Expenditures
Organization
Plans for Next Review

## Slide 44: Project Status – Overview
We are still on track for 2002 delivery – current ship date Oct 3
Critical path is Radiation Shield design and fabrication
Mechanism testing and bench integration is a close second
  Mechanism-to-bench fit checks are done
  Mechanism cold tests are beginning
  Bench integration completes in March
    Assembly of Post-Slit bench
      Bench +Prism, Grating and Camera Turrets, Acquisition Mirror and Collimator
    Assembly of Pre-Slit bench
      FW, Slit/Decker, and fore-optics
    Mating of Pre-Slit, OIWFS and Post-Slit benches
Software and electronics are working
  Test and debug completed
  Software checks with actual hardware in process
OIWFS integration is complete
  Detector installation remains to be done at a later date

## Slide 45: Project Status – WBS 5.2 Systems Engineering
All planned tasks in this work element are complete
Activities over this quarter included
  Oversight of the top level design and interfaces
  Coordination of mechanism cleaning and assembly
  Mechanism warm tests
  Mechanism flexure tests
  Fore-optics testing
  Resources
    1.5 Scientists

## Slide 46: Project Status – WBS 5.3 Mechanical
Mechanism %
Camera 99
Detector Focus 92
Environ Cover 99
Acquisition Mirror 89
Slit Decker 95
Filter Wheel 95
Grating Turret 98
Gratings 100
Prism Turret 95
Prisms 100
Motor Drives 100
Bench %
Post-Slit 100
OIWFS 100
Collimator 95
POM/Offner 100
Fixed Assembly %
Entrance Window 100
Cryo-cooler 59
Molecular Sieve 100
Thermal Dist. 75
LN2 Pre-Cool 83
Opt Bench Mount 100
Environ Cover Filter 100
Bulkhead 100
Passive Rad Shield 68
Active Rad Shield 17
Front Dewar Shell 100
Rear dewar Shell 100
Vert Inst Frame 100
Horiz Inst Frame 100
Dewar Mount Truss 100
TE Mount Truss 100
Shipping Container 0
Handling Fixture 100
Ballast Weights 100

## Slide 47: Project Status – WBS 5.3 Mechanical
All mechanism fabrication complete
  Only activity is in rework of items found in testing
Collimator assembly complete – waiting assembly/alignment
Fixed assembly 3D/2D design and fabrication remaining
  Radiation shields (passive and active)
  Thermal distribution assembly
  Cryo-cooler and manifold
Resources
  2 ME’s, 3 MD, 4 IM, 1 M&P Eng, 1 Procurement

## Slide 48: Project Status – WBS 5.4 Electrical
Design activities are completed
Instrument Controller electronics thermal enclosure complete
Work remaining
  Fabricate the Thermal Enclosure to Dewar cables
  Harness the cold mechanisms and cold bench as they become available
  Support software testing
  Harness the Bulkhead Assembly
  Dewar warm-up controller fabrication
Resources
  0.25 EE, 1 ET

## Slide 49: Project Status – WBS 5.5 Software
Component Controller code complete
  Code has been tested as far as possible before integration
  Testing with mechanisms is underway
    Lookup tables for individual mechanisms remain
  Array controller code interface is yet to be verified
High level (EPICS) code 99% complete
Resources
  1 SE

## Slide 50: Project Status – WBS 5.8 Procurement
Major items remaining in procurement
  Passive and Active radiation shields
  Cryo-cooler assembly
  LN2 Pre-cool assembly
There are no major vendor fabrication contracts
  Remaining work is radiation shields and small parts/components
Resources
  1 Tech Associate, production

## Slide 51: Project Status – Optics
Instrument optics procurement complete
  Optics for Telescope Simulator remain
Filters (still an open item)
  7 filters ordered through UH consortium; 2 failed spec and vendor may replace
Tasks left include
  Camera alignment(s)
  Collimator alignment
  Optics alignment tests of assembled benches
Resources
  1 Optical Tech, 0.25 OE

## Slide 52
This Page Intentionally Left Blank

## Slide 53: Project Milestones by Quarter
As of 1/16/02

## Slide 56: Planned FTE Projection

## Slide 57: FTE Projection
Table shows the resources forecast through delivery and training
Approximately 16,600 hrs total needed to finish the project
  This does not include commissioning or the impact of the pending change order for delivery to Chile

## Slide 60: Organization Chart

## Slide 61
Director, NOAO
J. Mould
Gemini Projects
Project Manager
N. Gaughan
Administrative Assistant
M. Bowersock
Project Scientist, Systems Engineering
J. Elias
Mechanical Engineers
G. Muller
Optical
Engineer
M. Liang
Electrical Engineer
J. Penegor
Mechanical Designers
J. Andrew
D. Rosin
E. Downey
Programmer
P. Ruckle
Project Assistant
D. Eklund (.5)
Electrical Tech
R. George
Support Scientists
D. Joyce
B. Gregory
Procurement & Vender Liaison
A. Davis
ETS
L. Daggert
General Technician
J. Pina
Instrument Makers
J. Stein
R. Bennett
R. Harris
J. Irvine
M&P
B. Ditsler

## Slide 62: Plans for Next Review
The next Quarterly Review will be held in the April 2002 timeframe
The project will be into the Integration and Test Phase
  Flexure testing planned start in late April
Mechanical design will be complete
Mechanical fabrication will be complete
  except for items associated with flexure testing and shipping container
  Some rework items as identified in integration may remain
Electronics fabrication and checkout completed
  Some rework items as identified in integration may remain
Component Controller Software completed and operating with the Electronics
  EPICS level software will still be in work
OIWFS integration will be completed
Manuals will have started
  Outlines will be done
  Manual drafts will have started

## Slide 63: Conclusions
The current project status shows us to be over 86% complete
We are on track to deliver in October 2002
We are near the end of the design phase
  Radiation shield design is taking longer than anticipated
  Mechanism testing and rework is taking longer than planned
We are near the end of the fabrication phase
All mechanisms have passed warm functional and flexure tests
  Exception is focus mechanism which has yet to be fully tested
The estimated cost of GNIRS is $ 4,371,585
  January ’99 to delivery

## Slide 64: Appendix A – Images Appendix B – Milestones, WBS Chart

## Slide 65: Appendix A
Configuration and
Fabrication Images

## Slide 66: OIWFS with Assemblies

## Slide 67: Complete Foreoptics Assembly

## Slide 68: Short Cameras Fit-Checked on Turret

## Slide 69: Four Cameras – Long Blue and Red (far left and right) and Short Blue and Red (center)

## Slide 70: Detector Focus Frame Assembly

## Slide 71: Grating & Prism Turrets and Cold Test Fixtures

## Slide 72: Grating Turret Fit Check into Optical Bench

## Slide 73: Pre-Slit Bench Fit Check

## Slide 74: Prism Turret Mounted to Cold Test Fixture

## Slide 75: Slit Slide Fit Check

## Slide 76: Optical Bench Preliminary Fit Check
Ed Hileman

## Slide 77: Optical Bench Fit Check & Team
Randy Bennett, Ed Hileman, Al Davis, John Stein, Gary Muller, Dick Joyce, John Andrew

## Slide 78: View down Collimator to Optical Path

## Slide 79: Assembled Bulkheads & Dewar Shells before Painting

## Slide 80: Vacuum Testing of Chamber

## Slide 81: Tangent Bars & Collimator Gimbal Mount Ring

## Slide 82: Bulkhead after Painting

## Slide 83: Bulkhead Detail

## Slide 84: Bulkheads being Assembled
Al Davis, Gary Muller

## Slide 85: Fully Assembled Bulkhead & Dewar Shells
Ed Hileman

## Slide 86: Full Assembly on Handling Cart

## Slide 87: Appendix B
Milestones
WBS Chart

## Slide 88: Milestones since MFR (3/01)

## Slide 89
WBS - Total Project

## Slide 90
This Page Intentionally Left Blank