## Slide 1
QUARTERLY REVIEW
May 1, 2002

## Slide 2
This page intentionally left blank

## Slide 3: GNIRS Quarterly Review
Table of Contents
Introduction Pg 4
Progress Overview Pg 5
Technical Presentation Pg 7
Project Management Pg 23
Appendices Pg 53

## Slide 4: Introduction
This is the 8th GNIRS Quarterly Review
GNIRS is in the assembly and integration phase
  Fabrication is complete
    Any further modifications, etc. are considered part of integration
  Mechanism testing is almost complete
    Final mechanism (Focus assembly) in cold test
  OIWFS integration is complete
Delivery is now scheduled for late November of 2002
  Delays in subassembly testing and rework
  Delays in fabrication of shields
  Flexure test facility will be late coming on line

## Slide 5: Progress Overview
The project is currently 91% complete overall
We have completed 195 of 225 total project milestones
Major activities over this quarter:
  Mechanism testing
  Design cleanup and final parts fabrication
    Fine tuning and correction of errors
  Shield fabrication
  Bench assembly and wiring
  Software code
    Component Controller code complete
    EPICS software complete
    Any further code changes will be considered part of integration/test

## Slide 6
This page intentionally left blank

## Slide 7: Technical Presentation
Subassembly testing
Integration procedures
Telescope simulator
Flexure testing
Configuration update

## Slide 8: Subassembly Testing
Mechanism warm tests
  Configuration time, repeatability, flexure
Mechanism cold tests
  Configuration time, repeatability
Optical assembly tests
  Wavefront error, alignment

## Slide 10
This page intentionally left blank

## Slide 12: Instrument Assembly

## Slide 13
Top Assembly Integration Plan

## Slide 14: Telescope Simulator
Beam simulator is GNIRS test fixture, not facility simulator
  Simulates Gemini telescope beam, including pupil
  Field of view ~30 mm
  1-5 microns wavelength
  Support XYZ stage with integrating sphere, light source and pinhole masks

## Slide 15: Telescope Simulator

## Slide 16: Telescope Simulator
Flex rig simulates telescope motion
  180 degree rotation about elevation axis, optical axis
  Sample 90 degree increments for initial tests
  Sample 30-45 degree increments for full flexure map

## Slide 17: Flexure Rig

## Slide 18: Flexure Testing
Displacement of telescope pupil on cold stop
  Requirement 1% or less
  Measure with pupil viewer

## Slide 19: Flexure Testing
Slit-to-detector flexure
  0.1 pixel.hour = 0.4 pixel/unit gravity
  Measure with pinhole arrays in slit mask
  Measure with long and short cameras
  Adjust calibration for compensation at collimator

## Slide 20: Flexure Testing
OIWFS to slit
  10 microns/hour
  Use dual pinhole mask, image one hole in each channel, displace mask to keep OIWFS image centered (“guiding”)

## Slide 21: Configuration Update
Weight and CG
  Revised Value = 4094 lb
    limit = 4409 lb
    increase 42 lb from last QR, -19 lb from 3/01
    Change mainly due to shields, hence only small c.g. change
  Spot check hardware against models
    true weights within 2% of models
Drawing status
  1508 drawings released of 1613 total

## Slide 22
This page intentionally left blank

## Slide 23: Project Management
Summary Overview
Last QR response
Schedule update
Current integration plan
Cost and Schedule
  Current progress
  WBS report
  Work/FTE projections
  Capital
  Cost to complete projection
  Milestones
  Deliverables projections
  Gemini payments summary
Work still outstanding
  Telescope simulator
  Outstanding fabrication
  Electronics and software
Problems and Concerns
  SRC lens
  Collimator mirror
  IFU late delivery
  OIWFS prism integration
Plans for Next Review

## Slide 24: Response to January QR
Items to be completed by this QR
  3D/2D design
  Mechanical fabrication
  Electrical fabrication and check-out
  Components controller software
  OIWFS integration/test
  Mechanism/optical testing
  Parts cleaning
  DPS Change Order
  Chile delivery Change Order

## Slide 25: January QR Response
ITEM | STATUS | COMMENT
3D/2D design | Complete | 
Mechanical fabrication | Complete | 
Electrical fabrication and check-out | Not Complete | Cables and Bulkhead wiring not completed
Components controller Software | Complete | 
OIWFS integration/test | Complete | Prism not available from Gemini
Mechanism testing | Not Complete | Slit and focus mechanisms still in test
Optical Testing | Complete | 
Parts cleaning | Not Complete | Some residual cleaning remains
DPS Change Order | Complete | 
Chile Delivery Change Order | Complete | 

## Slide 26: Schedule Update
Ship date has slipped to November 29th
  Mechanism testing and shield fabrication has taken much longer than planned
  Final block of schedule contingency is 4th cold test – 6 weeks
Critical path:
  Mechanism testing
  Dewar vacuum checks
  Instrument assembly and wiring
  Flexure testing
  SRC lens integration
  Cold testing

## Slide 27: Schedule Update
Top Assembly Integration should start by 15 May
  Component assembly onto bulkhead and benches
  Wiring
  Test
Flexure testing June 10-21
  Flexure acceptance has been delayed until 15 May.
  Rig installation may further delay testing
Cold testing and characterization from June – November
  Four cold cycle periods planned
  Last cycle is for contingency
Documentation deliverables have started and will complete during testing over the summer
  Three Manuals (hardware and software maintenance, operation)
  Design documentation

## Slide 28: Summary Project Plan

## Slide 29: Integration Plan

## Slide 30: Focus of Last Quarter of Work
Design/fabrication activity concentrated on
  Radiation shield fabrication
  Mechanism testing, rework
  Assembly cleaning and wiring
  Collimator assembly and mirror testing
  Telescope simulator design/fabrication
  General design cleanup (configuration control)
Procurement
  Mechanical
  Optical
    SRC lens
    Telescope simulator optics

## Slide 31: WBS Report - % Complete since MFR Mar ’01

## Slide 32: Budget and Expenditures

## Slide 33: Project Status – WBS 5.3 Mechanical
Mechanism %
Camera 100
Detector Focus 98
Environ Cover 100
Acquisition Mirror 100
Slit 95
Decker 100
Filter Wheel 100
Grating Turret 100
Gratings 100
Prism Turret 100
Prisms 100
Motor Drives 100
Bench %
Post-Slit 100
OIWFS 100
Collimator 100
POM/Offner 100
Fixed Assembly %
Entrance Window 100
Cryo-cooler 94
Molecular Sieve 100
Thermal Dist. 75
LN2 Pre-Cool 83
Opt Bench Mount 100
Environ Cover Filter 100
Bulkhead 100
Passive Rad Shield 100
Active Rad Shield 100
Front Dewar Shell 100
Rear dewar Shell 100
Vert Inst Frame 100
Horiz Inst Frame 100
Dewar Mount Truss 100
TE Mount Truss 100
Shipping Container 0
Handling Fixture 100
Ballast Weights 100

## Slide 34: Project Status – WBS 5.2 Systems Engineering
Activities over this quarter
  Mechanism testing
  Collimator mirror assembly testing
Work left
  Complete mechanism testing
  Oversee instrument assembly
  Integrate collimator assembly
  Flexure testing
  Cold testing
  Contribute to the Hardware Maintenance Manual
  Write the Operations Manual
Resources
    1.5 Scientists

## Slide 35: Project Status – WBS 5.3 Mechanical
All fabrication complete
  Only activity is rework found in testing/integration
  Telescope simulator still in fabrication
Assemblies in final processing
  Cyrocooler assembly cleaning, assembly, installation
  Thermal distribution copper strapping sizing and assembly
  Dewar wiring
  Radiation shield cleaning and assembly
3D/2D design complete
  Only clean-up items remain
Resources for this QR period
  2 ME’s, 3 MD, 4 IM, 1 M&P Eng, 1 Procurement
Resources after May 1st
  Part-time M&P for cleaning/assembly during top assembly integration
  1 ME, 2 MD, 2 IM, 1 Procurement

## Slide 36: Project Status – WBS 5.4 Electrical
Work Remaining
  Final mechanism testing support
  Assist in instrument assembly
  Fabricate the Thermal Enclosure to Dewar cables
  Harness the Bulkhead Assembly
Resources
  0.25 EE, 1 ET

## Slide 37: Project Status – WBS 5.5 Software
Component Controller code complete
EPICS code complete
Work remaining
  Participate in instrument assembly and checkout
  Complete Software Maintenance Manual
  Finalize code
Resources
  1 SE

## Slide 38: Project Status – WBS 5.8 Procurement
Procurement in process
  SRC lens
  Two gratings
  Simulator optics
  Miscellaneous mechanical items
Work remaining
  Complete optics procurement
  Records cleanup
  Participate in instrument assembly and checkout
Resources
  1 Tech Associate, production

## Slide 39: Project Status – Optics
Filters
  7 filters ordered through UH consortium; 2 failed spec and vendor may replace
  We will install what we have
Tasks left include
  Collimator testing, alignment and integration
  Install optics in Prism and Grating turrets
  Install filters
  SRC camera lens installation
  Grating installation
Resources
  1 Optical Tech, 0.25 OE

## Slide 42: Planned FTE Projection

## Slide 43: FTE Projection
Table shows the resources forecast through delivery and training
Approximately10,000 hrs total needed to finish the project
  This does not include commissioning or the impact of the pending change order for delivery to Chile

## Slide 46: Project Milestones by Quarter
As of 4/22/02

## Slide 47: Deliverables Projection
Documentation Draft Final
  Hardware Maintenance Manual June Aug
  Software Maintenance Manual July Sept
  Operations Manual Aug Oct
  As-Built Drawings Oct – Nov
Testing* Approx Scheduled Dates
  Pre-ship AT Nov 25
  Instrument Hardware Ship Nov 29
  Post –Ship AT Dec 16-17**
  Final AT Jan 6-31
  Commissioning Feb ’03
*Earlier if 4th cold test cycle not needed.
**Based on approval of Chile delivery change order

## Slide 48: Gemini Payments Summary – Current Work Scope
Milestone Payment Date
Original New
Test Plans Delivered $50,000* Mar-01 Mar-02
Parts Fabrication Complete 25,000 Jun-01 May-02
Manuals Complete 75,000 Aug-01 Oct-02
Warm Tests Complete 25,000 Dec-01 Jun-02
Cold Cycle Testing Complete 25,000 Mar-02 Sep-02
Pre-Ship Acceptance 80,000 Jun-02 Nov-02
Final Acceptance 300,857 Sep-02 Dec-02
Total $580,000
Change orders submitted
- DPS $ 2,683
- Chile Delivery 176,925
Total $179,618
*Billed to Gemini

## Slide 49: Work Still Outstanding
Design
  Documentation cleanup
  Assembly drawings
  As-built drawings
Assembly
  Bulkheads and shields
  Top assembly
Testing
  Vacuum tests
  Warm tests
  Flexure test
  Cold tests
Telescope simulator
  In fabrication, assembly/test
Collimator mirror
  Testing/characterization
Fabrication
  Cleanup miscellaneous items
  Documentation
Software
  Small code fixes as testing progresses
  Maintenance manual
Electronics
  Wiring and assembly
Mechanisms
  Focus cold test
  Slit rework and test
  Gratings and prism installations
  SRC lens replacement
Manuals
  Hardware/software maintenance
  Operation

## Slide 50: Problems and Concerns
No contingency left in the schedule
  Mechanism testing and shield fabrication took much longer than anticipated
Flex Rig installation schedule delay
  Moderate risk of impacting integration schedule
Short Red Camera lens replacement
  Lens will be received in June timeframe - integration at first opportunity
  Low schedule risk but requires complete instrument disassembly
Collimator mirror may degrade instrument performance
OIWFS prism
  Installation by Gemini after delivery and acceptance of instrument
  requires complete instrument disassembly by Gemini
IFU
  Delivery will be late - proceeding with mass model
  Low schedule risk – require only partial instrument disassembly

## Slide 51: Conclusions
The current project status shows us to be 91% complete
We are in the integration phase
  Focus mechanism testing in process
  Slit mechanism rework and retest
  Instrument top assembly is the next major activity
The next issue is flexure testing
  Facility delays are becoming a major concern
The estimated cost of GNIRS is $ 4,443,187
  January ’99 to delivery
  We are under budget on labor but over budget on capital
We have slipped schedule by 45 days
  There is no effective schedule contingency left

## Slide 52: Milestones for Next Review
The next Quarterly Review will be held in the August 2002 timeframe
Flexure testing will be complete
Two cold test cycles will have completed
Draft manuals will be complete and to Gemini for review
Design documentation deliverable will be complete
Shipping container
  Specified and designed
  Either in fabrication or in procurement

## Slide 53: Appendix A – Images Appendix B – Organization Chart Milestones WBS Chart

## Slide 54: Appendix A
Fabrication and Integration Images

## Slide 55: Full Assembly on Handling Cart

## Slide 56: Clean Room Assembly

## Slide 57: Camera Barrels

## Slide 58: Camera Test Fixture

## Slide 59: PreAmp Box

## Slide 60: Prism Turrets

## Slide 61: Active Shields

## Slide 62: Active Shields (cont)

## Slide 63: Appendix B
Organization Chart
Milestones
WBS Chart

## Slide 64
Director, NOAO
J. Mould
Gemini Projects
Project Manager
N. Gaughan
Administrative Assistant
M. Bowersock
Project Scientist, Systems Engineering
J. Elias
Mechanical Engineer
G. Muller
Optical
Engineer
M. Liang
Electrical Engineer
J. Penegor
Mechanical Designers
J. Andrew
D. Rosin
Programmer
P. Ruckle
Project Assistant
D. Eklund (.5)
Electrical Tech
R. George
Support Scientists
D. Joyce
B. Gregory
Procurement & Vender Liaison
A. Davis
ETS
L. Daggert
General Technician
J. Pina
Instrument Makers
J. Stein
R. Harris
M&P
B. Ditsler

## Slide 65: Milestones since MFR (3/01)

## Slide 66
WBS - Total Project