## Slide 1
QUARTERLY REVIEW
June 13, 2001

## Slide 2
This Page Intentionally Left Blank

## Slide 3: GNIRS Quarterly Review
Table of Contents
Introduction Pg 4
Project Summary Pg 7
Configuration & Integration Pg 23
Project Management Pg 43
Appendices Pg 65

## Slide 4: Introduction
This is the 5th GNIRS Quarterly Review
GNIRS is in the final design and fabrication phase
  Most of our “problems” are the delays in fabrication which affect our low-level test and integration schedules

## Slide 5: Outline
Project summary
  Last QR Response
  Progress Overview
  Cost and Schedule Status
Problems and Concerns
Integration plans
Project management
Plans for next review
Appendices

## Slide 6
This Page Intentionally Left Blank

## Slide 7: Project Summary
Response to last QR report
Progress overview
Summary schedule
Budget and expenditures to date

## Slide 8: Planned Completions by this Quarterly Review
Complete fabrication of all mechanisms
Complete design of all fixed assemblies
Complete lens delivery and acceptance testing
Complete dewar cold station PCB fabrication
Complete dewar warm-up controller fabrication
Complete dewar-to-thermal enclosure cabling

## Slide 9: Task Status
Item
Status
Comments
Complete fabrication of all mechanisms
Not Complete – two Camera Barrels, Focus Stage in detail design
Some rework will be required as testing progresses.
Complete design of all fixed assemblies
Not Complete – 10 of 19 fixed assemblies completed design
Should complete the design of the remaining items this quarter
Complete lens delivery and acceptance testing
Not complete - One BaF2 was broken by the vendor
Delivery of final lens is scheduled for August.
Complete dewar cold station PCB fabrication
Complete
Complete dewar warm-up controller fabrication
Not Complete – start of this activity has been rescheduled
Low priority activity that is not needed until late in the project.
Complete dewar-to-thermal enclosure cabling
Not Complete – design is complete
Actual fabrication waiting for final dimensions/length

## Slide 10: Exploded View

## Slide 11
Summary Project Plan

## Slide 12: Project Status - Progress from August ’99
  WBS element March Review June Review
  5.0 Overall project 53% 66%
  5.1 Management & Reporting 51% 61%
  5.2 Systems Engineering 100% 100%
  5.3 Mechanical 52% 70%
  5.3.1 Mechanisms 66% 84%
  5.3.2 Benches 55% 70%
  5.3.3 Fixed Assemblies 16% 36%
  5.4 Electronics 63% 59%
  5.5 Software 49% 63%
  5.6 Integration 0% 0%
  5.7 Deliverables 0% 0%
  5.8 Procurement 54% 67%

## Slide 13: Progress Overview
The August 2002 delivery date of the instrument has not changed
The project is currently 66% complete overall
  We are in the fabrication phase and in process of completing final design tasks
We have completed 92 of 224 total project milestones
Our critical path is completing 2D design and fabrication of fixed assemblies
Optics are either complete or in fabrication
Mechanical
  Mechanism fabrication is essentially complete
  Bench fabrication is near completion
  All cold structure 3D design is complete
  10 fixed assemblies remain to be designed
Electronics fabrication is 2/3 complete
Software low-level code development is in test
  EPICS code is in work

## Slide 14
Collimator Passive Compensation

## Slide 15: Comments on last quarter of work
Design activity concentrated on
  the Bulkhead Assembly design and release to fabrication
  Detector-Focus Assembly design and release to fabrication
  Passive Collimator 3D design
  Start of Fixed Assembly design
Fabrication – both in-house and vendor contracted
  Mechanical and electrical
Detail planning for mechanism test and integration
Interface issues and the envelope waiver

## Slide 16
This Page Intentionally Left Blank

## Slide 17: Progress and Schedule Comments – The bottom line
There are no known technical issues left to address
We will enter the integration phase of the project about 6 weeks late
  Delaying integration has not impacted our fall-2002 delivery
  The first 3 months of integration schedule is flexible with respect to integrating different mechanisms and assemblies
  We still have contingency built into the integration schedule
The mechanical design effort is going extremely well but is taking longer than planned
  3D design is nearly complete – <10 fixed assemblies remain
  2D detailing is the critical effort - should complete by mid-July
Fabrication is running late on several key assemblies
  Primarily due to vendor delays
  This has impacted mechanism assembly/test
  Fabrication will continue through September - October
Mechanism assembly/test has slipped to summer

## Slide 18
This Page Intentionally Left Blank

## Slide 19: Budget and Expenditures
Baseline Estimate (Jan 99 to completion)
  Labor $3,391,232
  Capital $ 836,462
  Total $4,227,694
Current Forecast
        March Review June Review
  Labor $2,866,775 $3,002,938
  Capital $1,074,798 $1,181,900
  Total $3,941,573 $4,184,838
Performance ratios
        March Review June Review
    BCWS $ 1,754,979 $ 2,863,855
    BCWP $ 1,611,542 $ 2,011,383
    ACWP $ 1,742,651 $ 2,113,212
    CPI 0.92 0.95
    SPI 0.92 0.70

## Slide 20
This Page Intentionally Left Blank

## Slide 21: Problems and Concerns
Fabrication delays
  Vendor schedule performance issues are threatening to delay mechanism testing and integration schedules
  Amount of rework is yet unknown w/respect to schedule allowance
OIWFS component late delivery
  Will cause resources to be diverted from other activities to work on OIWFS integration and test
  Scheduled delivery continues to slip
IFU delivery will not occur as planned
  We will use mass models instead of the real units
  Integration at a late date will be complicated
Flexure test rig on line by date needed (mid-February, 2002)

## Slide 22
This Page Intentionally Left Blank

## Slide 23: Configuration Overview
Envelope
Weight and C.G. estimate
Movement range of electronics boxes

## Slide 25: Configuration - Overview
Dewar and trusses fully defined
  Check/deal with envelope violations
  Weight and c.g. uncertainty reduced

## Slide 26
(envelope image)

## Slide 27: Configuration - Envelope
Envelope waiver negotiated with Gemini
  Intrusion into rear dealt with by removable installation truss (normally removed)
  Intrusion into “underside” dealt with by removable installation truss (normally installed)
  Intrusion into service area near ISS dealt with by waiver

## Slide 28: Configuration - Weight
Weight is under control
  Weight requirement (budget): 4413 lb
  Weight estimate 3/01: 4115 lb
  Weight estimate 6/01: 3930 lb
  Estimated ~100 lb uncertainty through integration

## Slide 29: Configuration - C. G.
C. G. under control
  Requirement z=100 cm, x,y=0
  March/01 z=105 cm, x=4 cm, y=5 cm (4100 lb: error ~630 ft-lb = 860 N-m)
  June/01 z=104 cm, x=0, y=-3 cm (3930 lb: error about the same)
  Electronics enclosures can be shifted in z, increment ~40 ft-lb

## Slide 30
This Page Intentionally Left Blank

## Slide 31: Configuration - Ballast
Ballast will be needed
  Weight estimate implies need; include ballast points in design
  C. G. correction will use <300 lb
  Additional ballast will be used to “trim” instrument as required

## Slide 32: Integration Overview
Subsystem testing qualifies individual mechanisms and optical assemblies
Integration into bench permits check of warm optics and mechanisms
Integration of cold structure into dewar for vacuum, cryo testing
Final tests

## Slide 33: Integration Overview
Subsystem testing
Bench integration/test
Dewar integration

## Slide 34: Subsystem Testing
Qualifies sub-assemblies for integration
  Performance can be checked prior to final integration
  Problems are isolated
  Maximum time for problem fixes

## Slide 35: Subsystem Testing
Testing of mechanisms as outlined in previous reviews
  Warm functionality
  Warm flexure
  Cold functionality
  Tests (esp. cold tests) without optics

## Slide 36: Subsystem Testing
Optics testing of “powered” sub-assemblies
  Four cameras
  Offner relay
  Verifies performance, not required for alignment
  Camera tests require calculation of thermal, wavelength shifts

## Slide 37: Bench Integration
Add subsystems to bench after qualification
  Main bench completes in late July; clean and paint after fit checks
  Integrate prism turret, acquisition mirror immediately
  Pre-slit assembly (Offner, filter wheels, slit/decker) integration and test complete early August
  Remaining mechanisms test and integration complete late August (short red camera may slip?)
  OIWFS assembly and alignment must be done by August

## Slide 38: Bench Integration
Integration into bench permits warm optics and mechanical check (uses warm MUX)
  Check (re-check) fit, alignment, repeatability
  Check image quality (“warm” predictions)
  Check flexure compensation calibration & performance (but not flexure calculations)

## Slide 39: Dewar Integration
Integration of cold structure into vacuum vessel
  prior test of vacuum integrity
  should be here at next QR
Re-test with MUX
  possible limited flexure test
Install engineering array

## Slide 40
This Page Intentionally Left Blank

## Slide 41: Dewar Integration
Initial cool-down followed by tests outlined in August ‘99 test plan
  start October
Opportunities for IFU installation during testing; schedule penalty varies

## Slide 42
This Page Intentionally Left Blank

## Slide 43: Project Management
Project Status
Schedule & Planning
Milestones
Budget and Expenditures
Organization
Plans for Next Review

## Slide 44
This Page Intentionally Left Blank

## Slide 45: Project Status – WBS 5.2 Systems Engineering
Systems Engineering activities over this quarter included
  Oversight of the top level design and interfaces
  Completion of flexure testing/evaluation of rotary mechanism design approach
  Oversight of the passive collimator design
  Optical element evaluation
    Included prisms/gratings/mirrors/lenses
  Re-planning the initial phase of instrument integration
    In reaction to design and fabrication delays
  Envelope waiver submission

## Slide 46: Project Status – WBS 5.3 Mechanical
Mechanism %
Camera 89
Detector Focus 46
Environ Cover 99
Acquisition Mirror 75
Slit Decker 85
Filter Wheel 83
Grating Turret 85
Gratings 86
Prism Turret 74
Prisms 74
Motor Drives 98
Bench %
Post-Slit 69
OIWFS 86
Collimator 45
POM/Offner 81
Fixed Assembly %
Entrance Window 100
Cryo-cooler 18
Thermal Dist. 0
Bulkhead Rad Shield 0
LN2 Pre-Cool 84
Opt Bench Mount 43
Environ Cover Filter 0
Bulkhead 57
Front Rad Shield 3
Rear Rad Shield 0
Front Dewar Shell 37
Rear dewar Shell 26
Vert Inst Frame 17
Horiz Inst Frame 5
Dewar Mount Truss 23
TE Mount Truss 53
Shipping Container 0
Handling Fixture 68

## Slide 47: Project Status – WBS 5.3 Mechanical
All mechanisms are in fabrication except two camera barrels and the focus stage.
All optical benches are in fabrication
Fixed assembly 3D design remaining
  Front/rear dewar shells
  Radiation shields (4)
  Thermal distribution assembly
  Cryo-cooler and manifold
  LN2 Pre-cool assembly
Fixed assembly 2D detailing in-work
  Detector mount assembly
  Vertical and Horizontal installation frames
  Dewar mount truss assembly
  Thermal enclosure mount assembly

## Slide 48: Project Status – WBS 5.4 Electrical
Design activities are completed
  schematic and parts list updates occur as needed
Fabrication in progress
  Ancillary Crate is being assembled and harnessed, will be completed and tested in June 2001
  final Component Controller crate (WFS Phytrons) to be delivered
  1/3 of Component Controller internal harnessing is done
Work Remaining
  assemble and clean the Coldstation PCBs
  finish the Thermal Enclosure internal harnessing
  fab the TE to Dewar cables (are all simple 1:1 cables)
  harness the Cold Mechanisms and Cold Bench as they become available

## Slide 49: Project Status – WBS 5.5 Software
Component Controller code 90% complete
  Code has been tested as far as possible
  Waiting for
    Completion of the electronics thermal enclosure
    Actual mechanisms
High level (EPICS) code 70% complete
Gemini DHS received, being evaluated

## Slide 50: Project Status – WBS 5.8 Procurement

## Slide 51: Project Status –Optics
Lenses and Windows
  Only one BaF2 lens for short red camera remains
    Vendor remaking the last lens
Mirrors
  All mirrors received except for POM and Acq Mirror
    POM and Acq Mirror are replicas, due in 4 weeks
    Flats are due in 3 weeks
Gratings
  2 Gratings in fabrication, due the end of June; 3rd received
Filters
  7 filters ordered through UH consortium; 2 failed spec and vendor is expected to replace
Prisms
  Wollaston prism due in 2nd half of August
  Cross-dispersion prisms due late July

## Slide 52
This Page Intentionally Left Blank

## Slide 53: Project Milestones by Quarter
As of 6/8/01

## Slide 54
Work Package Status 8/99 thru 5/01

## Slide 55
WBS - Total Project

## Slide 60
This Page Intentionally Left Blank

## Slide 61
Gemini Projects
Project Manager
N. Gaughan
Director, NOAO
J. Mould
Project Assistant
D. Eklund (.5)
Administrative Assistant
M. Bowersock
Project Scientist,
Systems Engineering
J. Elias
J. Elias
Mechanical Engineers
E. Hileman
G. Muller
Electrical Engineer
J. Penegor
J. Elias
Optical Engineer
M. Liang
Procurement & Vendor Liaison
A. Davis
Software
R. Wolff
Support Scientists
D. Joyce
B. Gregory
Mechanical Designers
J. Andrew
D. Rosin
E. Downey
D. Circle
Electrical Technicians
R. George
Intern
A. Lowe
Staff Added: R. Bennett, L. Lederer, R. Davis, Interns S. Kroto, E. Mountford, A. Lowe
Staff Transferred: R. Robles
Updated 6/01
General Technician
J. Pina
Intern
S. Kroto
Programmer
P. Ruckle
Instrument Maker
J. Stein
R. Bennett
L. Lederer
R. Davis
Intern
E. Mountford
M & P
B. Ditsler

## Slide 62: Plans for Next Review
The Next Quarterly Review will be held in the September timeframe
We will make significant progress in mechanism and optical subassembly testing
All optics to be received
  Flats/Prisms/Grating replicas
Final mechanical assemblies to have completed fabrication
  Bulkhead assembly (to be undergoing testing at vendor)
  Dewar components (rad shields, shells, etc.)
  Mounting trusses
  Cryo hardware
Electronics enclosure fabrication and checkout completed
Final Component Controller Software testing will be in process
OIWFS components integration/test should be completed

## Slide 63: Conclusions
The current project status shows us to be 66% complete
We will complete the design phase over the next quarter
We are firmly into the fabrication phase of the plan
We are about 6 weeks behind baseline schedule
We are on track to deliver in fall 2002
The estimated cost of GNIRS is not significantly changed from the August ’99 baseline
  Estimated total cost: $4,184,838 - January ’99 to delivery

## Slide 64
This Page Intentionally Left Blank

## Slide 65: Appendix A – Images Appendix B – Milestones Appendix C – Envelope Waiver

## Slide 66: Appendix A
Configuration and Fabrication
Images

## Slide 67: Top Assembly

## Slide 68: Top Assembly

## Slide 69: Exploded View

## Slide 70: Top Camera Cover

## Slide 71: Tangent Support Bar Bracket

## Slide 72: Slit Decker Housing

## Slide 73: Pickoff Mirror Housing

## Slide 74: Pre-Slit Bench Aft Housing

## Slide 75: Lower Slit Slide Rail

## Slide 76: Slit Slide Assembly

## Slide 77: Prism Turret Drive Assembly

## Slide 78: Grating Turret Drive Assembly

## Slide 79: Offner Assembly

## Slide 80
This Page Intentionally Left Blank

## Slide 81: Appendix B
Milestones

## Slide 82
This Page Intentionally Left Blank

## Slide 83: Milestones since MFR (3/01)

## Slide 84
This Page Intentionally Left Blank

## Slide 85: Appendix C
Envelope Waiver